## User Stories Backlog
Feature Backlog
ID | Description | Status
US1 | As a user, I want to submit orders – for ordering food online. | Complete
US2 | As a user, I want to modify and cancel orders in progress – for changing my mind. | Backlogged
US3 | As a user, I want a short window for cancelling submitted orders – for change of plans. | Backlogged
US4 | As a developer, I want a unified database – for connecting users and kitchen staff to orders. | Complete
US5 | As an administrator, I want to create, read, update, and hide available items – for changes to the kitchen menu and item availability. | Complete
US6 | As an administrator, I want to change ordering hours – for changes to the restaurant hours. | Complete
US7 | As a cook, I want a simplified order screen – for tracking orders in progress. | Complete
US8 | As a cook, I want to cancel submitted orders – for invalid orders or orders that cannot be fulfilled. | Complete
US9 | As a cook, I want to complete orders and notify customers – for clearing tickets and letting customers know their order is ready. | Complete
US10 | As an owner, I want daily reports on sales – for business needs and knowing which items are popular. | Backlogged
US11 | As a developer, I want a login system – for separating users, administrators, and kitchen staff. | Complete
US12 | As an owner, I want a third-party payment system – for processing payments securely, handling refunds, and securing user payment information offsite. | Backlogged
US13 | As an owner, I want a donation option – for charitable donations direct to charities. | Backlogged
US14 | As a user, I want an account – for tracking current and previous orders. | Complete
US15 | As a user, I want the site to be accessible – for accommodating disabilities. | Backlogged
US16 | As a user, I want the site to be secure – for protecting my privacy and login information. | Complete
US17 | As a developer, I want unit tests – for checking the system is functional after changes are implemented. | Complete

## Non-Functional Requirements
Non-Functional Requirements
ID | Description | User Story ID(s) | Status
NFR1 | Users can create and access an account for order tracking | US2, US3, US9, US11, US14 | Complete
NFR2 | Users can create, read, update, and delete new orders | US1, US2, US3 | Complete
NFR3 | Users can cancel submitted orders for a short time after submission | US3 | Backlogged
NFR4 | Users can opt to create a charitable donation when processing their payment | US13 | Backlogged
NFR5 | Kitchen staff can track orders in progress | US7 | Complete
NFR6 | Kitchen staff can cancel submitted orders | US8 | Complete
NFR7 | Kitchen staff can complete orders and notify customers | US9 | Complete
NFR8 | Users can receive a notification that their order is ready | US9 | Complete
NFR9 | Administrators can create, read, update, and hide items available on the menu | US5 | Complete
NFR10 | Administrators can update ordering hours | US6 | Complete
NFR11 | Administrators can generate or retrieve various reports | US10 | Backlogged
NFR12 | Users can access the site regardless of handicaps or device | US15 | Backlogged
NFR13 | Users can securely access the site | US16 | Complete
NFR14 | Users can pay through a third-party payment system | US12 | Backlogged
NFR15 | Developers can test by component | US17 | Complete

## Technical Requirements
Functional Requirements
ID | Description | User Story ID(s)
TR1 | Unified database for items, users, and orders | US4
TR2 | Website for allowing users to create, read, modify, and monitor orders; and create and login to account | US1, US14, US16
TR3 | Website for kitchen staff to view, cancel, and complete orders | US7, US8, US9
TR4 | Website for administrators to create, read, update, and hide items; and update store hours | US5, US6
TR5 | Link the systems using authentication to differentiate between front ends, update the database for each action, and allow users to track orders in progress | US1, US4, US5, US6, US7, US8, US9, US11, US14, US16

## Implementation Plan
Implementation Plan
ID | Non-Functional Requirement ID(s) | User Story ID(s) | Functional Requirement | Assignee | Estimate (hours) | Planned Start Date | Planned Completion Date | Status
SPR1 | 13 | 16 | Authentication database | Nicholas | 4 | 2025-10-20 | 2025-10-26 | Complete
SPR2 | 2 | 4 | Linked order database | Nicholas | 1 | 2025-10-20 | 2025-10-26 | Complete
SPR3 | 10 | 4 | Store settings database | Nicholas | 1 | 2025-10-20 | 2025-10-26 | Complete
SPR4 | 1, 13 | 14 | Registration view | Nicholas | 1 | 2025-10-20 | 2025-10-26 | Complete
SPR5 | 1, 13 | 14 | Login view | Nicholas | 1 | 2025-10-20 | 2025-10-26 | Complete
SPR6 | 2 | 1 | Menu display view for users | Nicholas | 2 | 2025-10-27 | 2025-11-02 | Complete | -4
SPR7 | 2 | 1 | Item modification view for users | Nicholas | 1 | 2025-10-27 | 2025-11-02 | Complete | -1
SPR8 | 2 | 1 | Cart view | Nicholas | 1 | 2025-11-03 | 2025-11-09 | Complete | -1
SPR9 | 2, 8 | 14 | Order tracking view for users | Nicholas | 2 | 2025-11-10 | 2025-11-16 | Complete | -1
SPR10 | 5 | 7 | Order tracking view for kitchen | Nicholas | 2 | 2025-11-17 | 2025-11-23 | Complete | -1
SPR11 | 7 | 9 | Past order view for kitchen | Nicholas | 1 | 2025-11-17 | 2025-11-23 | Complete | -2
SPR12 | 6, 7 | 9 | Selected order view for kitchen | Nicholas | 2 | 2025-11-17 | 2025-11-23 | Complete | -1
SPR13 | 9 | 5 | Menu display view for administrators | Nicholas | 4 | 2025-12-15 | 2025-12-21 | Complete | -1
SPR14 | 9 | 5 | Item creation/modification view | Nicholas | 2 | 2025-12-15 | 2025-12-21 | Complete | -2
SPR15 | 10 | 6 | Store settings view | Nicholas | 1 | 2025-11-24 | 2025-11-30 | Complete | -2
SPR16 | 13 | 16 | Authentication controller | Nicholas | 2 | 2025-10-20 | 2025-10-26 | Complete | -1
SPR17 | 2 | 1 | User controller - menu | Nicholas | 1 | 2025-11-24 | 2025-11-30 | Complete | -2
SPR18 | 2 | 1 | User controller - item modification GET and POST | Nicholas | 2 | 2025-12-01 | 2025-12-07 | Complete | -4
SPR19 | 2 | 1 | User controller - cart | Nicholas | 1 | 2025-12-01 | 2025-12-07 | Complete | -2
SPR20 | 2 | 1 | User controller - checkout | Nicholas | 1 | 2025-12-01 | 2025-12-07 | Complete | -1
SPR21 | 2 | 14 | User controller - past orders | Nicholas | 1 | 2025-12-08 | 2025-12-14 | Complete | -2
SPR22 | 2 | 1 | User controller - current order GET and POST | Nicholas | 2 | 2025-12-22 | 2025-12-28 | Complete | -1
SPR23 | 5 | 7 | Kitchen controller - order tracking | Nicholas | 1 | 2025-12-08 | 2025-12-14 | Complete | -2
SPR24 | 7 | 9 | Kitchen controller - past orders | Nicholas | 1 | 2025-12-08 | 2025-12-14 | Complete | -1
SPR25 | 5, 7 | 9 | Kitchen controller - selected order GET and POST | Nicholas | 2 | 2025-12-08 | 2025-12-14 | Complete | -1
SPR26 | 9 | 5 | Admin controller - menu | Nicholas | 1 | 2025-12-29 | 2026-01-04 | Complete
SPR27 | 9 | 5 | Admin controller - item creation/modification GET and POST | Nicholas | 2 | 2025-12-29 | 2026-01-04 | Complete | -1
SPR28 | 10 | 6 | Admin controller - Store settings GET and POST | Nicholas | 2 | 2025-12-29 | 2026-01-04 | Complete | -2
SPR29 | 13 | 16 | Authentication service - register and login | Nicholas | 4 | 2025-10-20 | 2025-10-26 | Complete | -1
SPR30 | 1 | 14 | User service - CRD | Nicholas | 2 | 2025-10-20 | 2025-10-26 | Complete | -1
SPR31 | 2, 9 | 1, 5 | Item service - CRUD | Nicholas | 4 | 2025-01-05 | 2025-01-11 | Complete | -2
SPR32 | 2, 9 | 1, 5 | Modification service - CRUD | Nicholas | 4 | 2025-01-12 | 2025-01-18 | Complete
SPR33 | 2, 3, 5, 6, 7, 8 | 1, 7-9, 14 | Order service - CRUD | Nicholas | 4 | 2025-01-12 | 2025-01-18 | Complete
SPR34 | 10 | 6 | Store service - CRUD | Nicholas | 2 | 2025-01-12 | 2025-01-18 | Complete | -1
SPR35 | 2, 9 | 17 | Item & Modification CRUD unit tests | Nicholas | 8 | 2025-01-19 | 2025-01-25 | Complete | -2
SPR36 | 2, 3, 5, 6, 7, 8 | 17 | Order CRUD unit tests | Nicholas | 2 | 2025-01-26 | 2025-02-01 | Complete | -2
SPR37 | 10 | 17 | Store settings CRUD unit test | Nicholas | 2 | 2025-02-02 | 2025-02-08 | Complete
SPR38 | 13 | 17 | Password encryption unit test | Nicholas | 1 | 2025-02-02 | 2025-02-08 | Complete | -4
-2
-4
-4
-4
-2
-8
-2
-2
Formulas:
Planned Completion Date = [Planned Start Date]+6

## Test Case #1
Project Name: |  | Online Food Portal
Module Name: |  | Item & Modification Services
Release Version: |  | 1.3
Test Designed By: |  | Nicholas Stanfill
Test Designed Date: |  | 2025-12-15
Test Executed By: |  | Nicholas Stanfill
Test Execution Date: |  | 2025-12-21
Test Case # | Test Title |  | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail Status | Notes
1 | Item/Modification CRUD |  | Navigate to <address>/Test Press [Item/Modification CRUD] | Item and modification are automatically generated and updated | Test Results: Pass 18 unit tests, each Pass | Test Results: Pass 18 unit tests, each Pass | PASS | The test is performed automatically with each change being verified by comparing the properties of the created object in memory and the retrieved object from the database The unit tests pass based on rows affected in the database or successfully comparing all properties Creates, reads, and updates an item Creates, reads, and updates a modification Deletes the modification, then recreates the modification Deletes the item, with cascade deleting the modification

## Test Case #2
Project Name: |  | Online Food Portal
Module Name: |  | Order Service
Release Version: |  | 1.3
Test Designed By: |  | Nicholas Stanfill
Test Designed Date: |  | 2025-12-15
Test Executed By: |  | Nicholas Stanfill
Test Execution Date: |  | 2025-12-21
Test Case # | Test Title |  | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail Status | Notes
2 | Order CRUD |  | Navigate to <address>/Test Press [Order CRUD] | Order is automatically created and updated | Test Results: Pass 6 unit tests, each Pass | Test Results: Pass 6 unit tests, each Pass | PASS | The test is performed automatically with each change being verified by comparing the properties of the created object in memory and the retrieved object from the database The unit tests pass based on rows affected in the database or successfully comparing all properties Creates, reads, updates, and deletes an order

## Test Case #3
Project Name: |  | Online Food Portal
Module Name: |  | Password Service
Release Version: |  | 1.3
Test Designed By: |  | Nicholas Stanfill
Test Designed Date: |  | 2025-12-15
Test Executed By: |  | Nicholas Stanfill
Test Execution Date: |  | 2025-12-21
Test Case # | Test Title |  | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail Status | Notes
3 | Password Encryption |  | Navigate to <address>/Test Press [Password Encryption] | The password is automatically generated | Test Results: Pass 2 unit tests, each Pass | Test Results: Pass 2 unit tests, each Pass | PASS | The test is performed automatically Generates a random password and encrypts the password If the generated password does not match the encrypted password, then the encryption is successful. Outputs the generated password and encrypted password If the generated password is verified as matching the encrypted password, the verification is successful

## Test Case #4
Project Name: |  | Online Food Portal
Module Name: |  | Store Settings Service
Release Version: |  | 1.3
Test Designed By: |  | Nicholas Stanfill
Test Designed Date: |  | 2025-12-15
Test Executed By: |  | Nicholas Stanfill
Test Execution Date: |  | 2025-12-21
Test Case # | Test Title |  | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail Status | Notes
4 | Store Settings RU |  | Navigate to <address>/Test Press [Store Settings RU] | The new store settings are automatically generated | Test Results: Pass 2 unit tests, each Pass | Test Results: Pass 2 unit tests, each Pass | PASS | The test is performed automatically. Creates a backup of the original settings and replaces them after the test The store settings are randomly generated, updated in the database, and verified through retrieval from the database

## Test Case #5
Project Name: |  | Online Food Portal
Module Name: |  | User Service
Release Version: |  | 1.3
Test Designed By: |  | Nicholas Stanfill
Test Designed Date: |  | 2025-12-15
Test Executed By: |  | Nicholas Stanfill
Test Execution Date: |  | 2025-12-21
Test Case # | Test Title |  | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail Status | Notes
5 | User CRD |  | Navigate to <address>/Test Press [User CRD] | The user is automatically generated with a random name to avoid affecting an existing user | Test Results: Pass 4 unit tests, each Pass | Test Results: Pass 4 unit tests, each Pass | PASS | The test is performed automatically Generates a random user, verifies the user exists in the database, deletes the user, and verifies the user no longer exists

## Test Case #6
Project Name: |  | Online Food Portal
Module Name: |  | ASP.NET Core Identity
Release Version: |  | 1.3
Test Designed By: |  | Nicholas Stanfill
Test Designed Date: |  | 2025-12-15
Test Executed By: |  | Nicholas Stanfill
Test Execution Date: |  | 2025-12-19
Test Case # | Test Title |  | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail Status | Notes
6 | User Registration and Login |  | Register as a new user Logout Log back in Navigate to other pages | Use a random username, it must be unique The other information can be the same | Username appears at the top after registeration, logging in, or navigating Username does not show when logged out | Username appears at the top after registeration, logging in, or navigating Username does not show when logged out | PASS | Confirms the ASP.Net Core Identity framework is using the MySQL server, cookies are used to maintain authentication, and the logout process functions Optionally, restart the application when logged in to confirm cookie functionality (PASS) Optionally, stop the application and wait 30 minutes before restarting to confirm cookie expiration (PASS) Optionally, wait 20 minutes after logging in to confirm cookie life before navigating then wait 20 more minutes before navigating to confirm sliding cookie expiration (PASS)